## Option 1
| PROJECT: |  | WEEKLY-TRACKED PROJECT
| Project Manager: |  | Your Name
| Today is | 2025-10-13
[6 empty] | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08
Task name | Stard date | End date | Planned Hours | Actual Hours | Progress | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27
Choose a Project | 2023-09-25 | 2023-09-30 | 4 | 4 | 100%
Task 1 | 2023-10-02 | 2023-10-07 | 8 | 7 | 87.5%
Task 2 | 2023-10-09 | 2023-10-14 | 8 | 9 | 112.5%
Task 3 | 2023-10-16 | 2023-10-21 | 10 | 7 | 70%
Subtask 3.1 | 2023-10-23 | 2023-10-28 | 10 | 9 | 90%
Study Week - 32 hours? | 2023-10-30 | 2023-11-04 | 30 |  | 0%
| 2023-11-06 | 2023-11-11 | 10 |  | 0%
| 2023-11-13 | 2023-11-18 | 10 |  | 0%
| 2023-11-20 | 2023-11-25 | 10 |  | 0%
Interim Report | 2023-11-27 | 2023-12-02 | 10 |  | 0%
| 2023-12-04 | 2023-12-09 | 10 |  | 0%
| 2023-12-11 | 2023-12-16 | 10 |  | 0%
Winter Exam Prep | 2023-12-18 | 2023-12-23 | 3 | 2 | 66.67%
Xmas | 2023-12-25 | 2023-12-30 | 0 |  | 0%
Winter Exam Prep | 2024-01-01 | 2024-01-06 | 0 | 0 | 0%
Winter Exam | 2024-01-08 | 2024-01-13 | 0 | 0 | 0%
Winter Exam | 2024-01-15 | 2024-01-20 | 0 | 0 | 0%
40 hours Possible here | 2024-01-22 | 2024-01-27 | 30 |  | 0%
| 2024-01-29 | 2024-02-03 | 10 |  | 0%
| 2024-02-05 | 2024-02-10 | 10 |  | 0%
| 2024-02-12 | 2024-02-17 | 10 |  | 0%
| 2024-02-19 | 2024-02-24 | 10 |  | 0%
| 2024-02-26 | 2024-03-02 | 10 |  | 0%
| 2024-03-04 | 2024-03-09 | 10 |  | 0%
| 2024-03-11 | 2024-03-16 | 10 |  | 0%
Proof-read thesis. Create Video | 2024-03-18 | 2024-03-23 | 10 |  | 0%
Study Week | 2024-03-25 | 2024-03-30 | 35 |  | 0%
|  | Total Hours | 278 | 38

## Option 2
PROJECT:
Project Manager:
Last revision:
Time: | 27 | hrs
Date | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Study | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Holiday | Holiday | Study | Exams | Exams | Break | Week 1 | Week 2 | Week 3 | Week 4
Choose a Project | 2 | 2
Submit interim report | [10 empty] | 8
Task 1
Task 2
Task 3
Proof-read thesis | [20 empty] | 2 | 2
Create video | [21 empty] | 6
Submit project | [22 empty] | 5
Suggested tasks
Literature review | 6 |  | 2 |  | 2
Background research
Create report template
Write introduction
Coding |  |  |  | 5 | 5 | 5 | 5 | 10
Write interim report | [8 empty] | 5
User testing
Unit testing | [7 empty] | 5
Refactoring code
Generate test data
Review/analyse data
Other assignments () | [8 empty] | 2 | 4 | 6 | 8 | 15
General Study